|  |  |  |
| --- | --- | --- |
| Task | Duration | Predecessors |
| A | 3 | - |
| B | 4 | A |
| C | 2 | A |
| D | 5 | B |
| E | 1 | C |
| F | 2 | C |
| G | 4 | D |
| H | 3 | E |

* Delivery day on day 19
* The task could be done without any delate except C, E and F.